Salmon sharks (Yannis)

Context for the collected data: This project uses biologging data, not telemetry. Tags are attached to salmon sharks for a few days and record continuous, high-resolution data. The loggers measure: Depth (≈1 Hz),  Tri-axial acceleration (20 Hz), Magnetometer for body orientation (20 Hz), Gyroscope for turning forces (20 Hz), Water temperature, Some individuals also have speed sensors.

Data come from only 2–3 sharks, but each recording is rich and long. Salmon sharks are close relatives of white sharks and are unusual because they are endothermic—their body temperature can be ~16°C warmer than the surrounding cold Alaskan waters.

Research question to answer: The project aims to identify daily activity patterns in salmon sharks and to examine how their behavior changes with time of day, depth, water temperature (key interest due to their endothermy). Also of interest: how well salmon sharks maintain activity in very cold water.

Possible challenges: Very small sample size (only 2–3 sharks). Need to treat acceleration, magnetometer, and gyroscope data carefully.

Expected timeline:

1.Data organization (1–2 weeks) – clean depth, acceleration, temperature, speed.

2.Exploratory analysis (1–2 weeks) – look for diel patterns, depth-use patterns.

3.HMM model setup (2 weeks) – choose variables (e.g ODBA, depth, temp), test different state numbers.

4.State decoding & interpretation (2–3 weeks) – identify active vs inactive states, cold-water behavior.

5.Ecological interpretation (1–2 weeks) – link activity with temperature and depth.

6.Final report (1 week) – summarize individual-based findings.